## Summary of HIRA
Summary of HIRA
|  | VEDANTA LIMITED – VALUE ADDED BUSINESS |  | Format No.: | FRMT/MR/22 |  |  |  |  | Trivial | 1-2 |  |  | Department Use only
[10 empty] | Acceptable | 3-4 |  |  | Dept | Mechanical
|  | INTEGRATED MANAGEMENT SYSTEM |  | Revision Date: | 04.04.2022 |  |  |  |  | Moderate | 5-9 |  |  | Unit | PID II
|  | RISK ASSESSMENT AND RISK CONTROL |  | Revision No.: | 2 |  |  |  |  | Substantial | 10-16 |  |  | Review Date | 24.08.2022
|  |  |  | Page No.: | 1 of 1 | RISK LEVEL WITH EXISTING CONTROL |  |  |  | Intolerable | 20-25 | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
SL no: | Activity | Types of Hazards | HAZARDS | RISK | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | Responsibity for Implementing the Opportunity Idenfied | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
1 | Distributor maintenance | Mechanical | 1. Fall of flange, bolts,wedges,rod etc. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Standard tools and tackles to use Proper Material handling techniques Skilled and competant person to carry out the job Safety Awareness/training Work procedure WI/BF3/06, SP 44,SP 46 | 1 | 2 | 2 | Nil
| Distributor maintenance | Mechanical | 2. Fall of person due to grease & oil spillage on platform | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Standard tools and tackles to use Proper Material handling techniques Skilled and competant person to carry out the job Safety Awareness/training Work procedure WI/BF3/06, SP 44,SP 46 | 1 | 2 | 2 | Nil
| Distributor maintenance | Mechanical | 3. Impact with structure due to lower head room. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Safety Awareness/training Work procedure WI/BF3/06, SP 44,SP 46 | 2 | 1 | 2 | Nil |  | PENDING
| Distributor maintenance | Physical | Pressure, temperature | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock Out Tag Out Skilled and competant person to carry out the job Work procedure WI/BF3/06,SP 44,SP 46 Safety Awareness/traning Use of PPE's | 1 | 2 | 2 | Nil
| Distributor maintenance | Chemical | Gas poisoning | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | usage of CO detector Steam purging of gas pipelines Work procedure SP 44,SP 46 , WI/MAINT/38 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Distributor maintenance | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Distributor maintenance | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Distributor maintenance | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Distributor maintenance | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Distributor maintenance | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
2 | HBS maintenance | Physical Hazard | 1. Pressure, temperature | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Physical Hazard | 2. Explosion in accumulators. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| HBS maintenance | Physical Hazard | 3. Explosion inside stove while doing cutting/welding activity | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 4 | 4 | Nil
| HBS maintenance | Physical Hazard | 4. Slip and fall due to oil spillage | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,,SP 44,SP 46, House keeping Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Physical Hazard | 5.Itching while handling of glass wool | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Safety Awareness/traning Use of PPE Work procedure WI/BF3/15,,SP 44,SP 46 | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 1.Trapping between two objects | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Physical fitness and competancy of the workmen Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 3 | 3 | Nil
| HBS maintenance | Mechanical Hazard | 2.Fall of material, hammer, tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 3.Failure of lifting machines, handling machines such as chain pulley block, sling, D shackle etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Testing of the tools at regular interval by external party Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 4.Fall of person from platform, heigh | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Strucral stability checking during erection Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 5.Entanglement of material | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 6.Impact of moving / slinged items | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/BF3/15,SP 44,SP 46 Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 7. Non use of PPE’s while carrying out the activity | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Deciplinary action | 1 | 2 | 2 | Nil
| HBS maintenance | Mechanical Hazard | 8.Snapping of hoist wire rope | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46, Inspection of wire rope and hook, Skilled Workmen | 1 | 2 | 2 | Nil
| HBS maintenance | Electrical hazard | Electric shock on equipment | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Electrical Shutdown Work procedure WI/BF3/15,SP 44,SP 46, Inspection of wire rope and hook, Skilled Workmen | 1 | 2 | 2 | Nil
| HBS maintenance | Chemical hazard | Co gas poisoning & Fire | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/15,SP 44,SP 46, Skilled Workmen | 2 | 3 | 6 | Inspection of wire rope and hook. | Mechanical |  | 1 | 3 | 3
| HBS maintenance | Chemical hazard | Explosion due to charging of impure N2 in accumulator | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | only 99.999% N2 cylinder to be used and certificate from suppler to be checked | 1 | 3 | 3 | Nil
| HBS maintenance | Behavioral Hazards | Alcoholism | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| HBS maintenance | Behavioral Hazards | Non usage of PPE's | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| HBS maintenance | Behavioral Hazards | Casual approach while working | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| HBS maintenance | Biological Hazard | Bee sting | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Inspection of areas before carring out job do do | 1 | 2 | 2 | Nil
3 | Drill bit fabrication | Physical Hazard | 1. Noise, vibration, pressure, temperature. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Physical Hazard | 2. Burn injury | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 1. Impingement of rod | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 2. Fall of pipe or tool | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 3. Fall of sparks in eyes, body, ear etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 4. Hitting of drill bit pipe | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 5. Slippage of pipe while handling | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Mechanical Hazard | 6. Skidding of person due to poor housekeeping. oil spillage, uneven surfaces, etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training,Use of PPE | 1 | 2 | 2 | Nil
| Drill bit fabrication | Electrical hazard | 1. Electric shock due to contact with open end cables & superficially laid underground electric cables. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Electrical shutdown, Work procedure WI/BF3/19,SP 44,SP 46,safety awareness training, | 1 | 2 | 2 | Nil
| Drill bit fabrication | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Drill bit fabrication | Behavioral Hazards | 2. Non usage of PPE's | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Drill bit fabrication | Behavioral Hazards | 3. Casual approach while working | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Drill bit fabrication | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
4 | GCP maintenance | Physical hazard | 1. Fire and Explosion. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Usage of CO detectorWork procedure WI/BF3/22,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 3 | 3 | Nil
| GCP maintenance | Physical hazard | 2. CO gas poisoning | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Usage of CO detectorWork procedure WI/BF3/22,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Physical hazard | 3. Suffocation due to insufficient oxygen. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | proper ventilation, on job training,Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Physical hazard | 4. Noise, vibration, pressure, temperature | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Physical hazard | 5. Slip and fall due to oil spillage. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Physical hazard | 6. Fall of dust in eyes, ears. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 1. Trapping between objects | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 3 | 3 | Nil
| GCP maintenance | Mechanical Hazard | 2. Falling of material from height | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Usage of certified Lifting tools & tackles Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 3. Falling of person from height | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 4. Fall of tools and tackles | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper handling of tools,safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 5. Impact of inspection doors while opening | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging,safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 6. Impact of slinged material | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Tesing of tools at regular interval by external patry,Proper slinging,safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 7. Crushing of person while lifting the material & fall | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 8. Fall while installation of Equipment | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 9. Trapping of person during the fall of material from height . | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | proper slinging of items,Skilled workmen,Use of PPE, | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 10. Failure of lifting machines, handling machines such as chain pulley block, sling, D shackle etc . | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE, timely inspection of lifting equipments. | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 11. Back Pain due to sudden or heavy load like check valve, motor | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 12. Cut from sharp edges of item | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| GCP maintenance | Mechanical Hazard | 13. Non use of PPE’s while carrying out the activity | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE, disciplinary action | 1 | 2 | 2 | Nil
| GCP maintenance | Electrical hazard | 1. Electric shock due to contact with open end cables & superficially laid underground electric cables. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Electrical shutdown | 1 | 2 | 2 | Nil
| GCP maintenance | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| GCP maintenance | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
5 | Lubrication | Mechanical hazards | 1. Trapping between the moving parts | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Physical fitness and competancy of the workmen Work procedure WI/MAINT/93,SP 44,SP 46 Safety Awareness /traning | 1 | 2 | 2 | Nil
| Lubrication | Mechanical hazards | 2. Impact of hammer, tools, components. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/MAINT/93,SP 44,SP 46 Safety Awareness /traning | 1 | 2 | 2 | Nil
| Lubrication | Mechanical hazards | 3. Fall of materials such as hammer, pipe wrench, spare parts, bolts, spanners, slinged items. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Lubrication | Mechanical hazards | 4. Entanglement between rotating components. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Lubrication | Physical Hazard | 1. Pressure of hydraulic oil. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Lubrication | Physical Hazard | 2. Temperature of oil. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Lubrication | Physical Hazard | 3. Fall of oil in eyes, ears, mouth | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Lubrication | Electrical hazard | 1. Electrical shock | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Lubrication | Chemical hazard | 1. Fire. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Lubrication | Chemical hazard | 2. Non use of PPE’s while carrying out the activity | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/93,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
6 | Scafolding procedure for painting ,piping & structural jobs. | Physical Hazard | 1. Noise, vibration, pressure, temperature. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure VL/IMS/VAB/WIMAINT103 ,SP 44,SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Physical Hazard | 2. Burn injury | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure VL/IMS/VAB/WIMAINT103 ,SP 44,SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 1. Impingement of rod | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44, SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 2. Fall of pipe or tool | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44, SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 3. Fall of sparks in eyes, body, ear etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 4. Hitting of drill bit pipe | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44 ,SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 5. Slippage of pipe while handling | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44, SP 46,safety awareness training, Use of PPE, House keeping | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Mechanical hazard | 6. Skidding of person due to poor housekeeping. oil spillage, uneven surfaces, etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/19,SP 44, SP 46,safety awareness training, Use of PPE, House keeping | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Electrical hazard | 1. Electric shock due to contact with open end cables & superficially laid underground electric cables. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Electrical shutdown, Work procedure WI/BF3/19,SP 44,SP 46, safety awareness training, | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Scafolding procedure for painting ,piping & structural jobs. | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
7 | Blow pipe replacement | Physical Hazard | 1. Pressure, temperature | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Blow pipe replacement | Mechanical hazard | 1. Trapping between two objects | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Blow pipe replacement | Mechanical hazard | 2. Fall of material, hammer, tools, slinged items, bolts, blowpipe, wedges | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Blow pipe replacement | Mechanical hazard | 3. Fall of person from platform, | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 4 | 4 | Nil
| Blow pipe replacement | Mechanical hazard | 4. Entanglement | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Blow pipe replacement | Mechanical hazard | 5. Impact of moving / slinged items | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Blow pipe replacement | Mechanical hazard | Back Pain due to sudden or heavy load like blow pipe elbow | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Alloting job as per Healtheness of workmen Safety Awareness/traning Use of PPE | 1 | 1 | 1 | Nil
| Blow pipe replacement | Mechanical hazard | Non use of PPE’s while carrying out the activity | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/11,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Deciplinary action | 1 | 2 | 2 | Nil
| Blow pipe replacement | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Blow pipe replacement | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Blow pipe replacement | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 1 | 1 | Nil
| Blow pipe replacement | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
| Blow pipe replacement | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
8 | Peephole flange opening & Closing | Mechanical hazard | Trapping of hand between blow pipe flange and peep hole assembly | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Physical fitness and competancy of the workmen Work procedure WI/MAINT/54,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Mechanical hazard | Impact | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/MAINT/54,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Mechanical hazard | Entangement | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Proper slinging Work procedure WI/MAINT/54,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Mechanical hazard | Falling of peep hole flange, wedge and pins | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Testing of the tools at regular interval by external party Usage of correct size pin & wedges Work procedure WI/MAINT/54,SP 44,SP 46 Safety Awareness /traning Use of PPE | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Mechanical hazard | Human behaviour | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/54,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Deciplinary action | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Physical Hazard | Temperature of blow pipe | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/54,SP 44, SP 46 Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Peephole flange opening & Closing | Chemical hazard | Gas poisoning | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/54,SP 44, SP 46 Usage of CO monitor Safety Awareness/traning Use of PPE | 1 | 3 | 3 | Nil
| Peephole flange opening & Closing | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
| Peephole flange opening & Closing | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Peephole flange opening & Closing | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
| Peephole flange opening & Closing | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
9 | Bleeder valve maintenance | Mechanical hazard | 1. Trapping between two objects | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 2. Fall of material, hammer, tools, slinged items, bolts. | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 3. Fall of person from platform. | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 2 | 2 | 4 | Nil
| Bleeder valve maintenance | Mechanical hazard | 4. Entanglement of person in gas cutting and weldingcables | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 5. Human behavior aspect of contract employees | Serious Injury / LTI / MTI | contractor employees Supervisors | Skilled Workmen Safety Awareness/traning Usage of safety harness Use of PPE Diciplinery action | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 6. Pipe, wedges, | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 7. Impact of moving / slinged items | Serious Injury / LTI / MTI | Workmen/Subcontractor on the Job | Work Instruction/PPE's | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Mechanical hazard | 8.Contact with hot surface and cutout patch | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Physical Hazard | Pressure, temperature | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Physical Hazard | Explosion while gas cutting operation | Serious Injury / LTI / MTI | contractor employees | Work procedure WI/MAINT/46, WI/MAINT/94,SP 44,SP 46 | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Chemical hazard | 1. Gas poisoning, Fire | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Electrical hazard | 1. electrical shock | Serious Injury / LTI / MTI | contractor employees | Work Instruction/PPE's | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Bleeder valve maintenance | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
| Bleeder valve maintenance | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 3 | 3 | Nil
10 | Furnace top hatch opening & closing | Mechanical Hazard | Fall of flange, bolts, wedges, rod etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/94,SP 44, SP 46 Safety Awareness/traning Use of PPE | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Mechanical Hazard | Fall of person | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/94,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Usage of safety hardner | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Physical hazard | Explosion, fire, temperature, Pressure | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/94,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Usage of safety hardne | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Chemical hazard | Gas poisoning | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/MAINT/94,SP 44, SP 46 Skilled Workmen Safety Awareness/traning Use of PPE Usage of safety hardne Usage of CO monitor Opening all hatches | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 2 | 2 | 4 | Nil
| Furnace top hatch opening & closing | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 2 | 2 | 4 | Nil
11 | Stock rod maintenance | Mechanical hazard | Fall of equipment / person from height | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Use of PPE Usage of full body harness Proper Material handling techniques Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Mechanical hazard | Trapping between two objects | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock Out Tag Out Skilled and competant person to carry out the job Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Mechanical hazard | Fall of material, hammer, tools, slinged items, | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Standard tools and tackles to use Proper Material handling techniques Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Mechanical hazard | Fall of bolts, wedges, stock rod, pulley | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | barricading the area Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Mechanical hazard | Entanglement | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock Out Tag Out Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Mechanical hazard | Impact of moving / slinged items | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Standard tools and tackles to use Proper Material handling techniques Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Human behavior | Aspect of contract employees ,alcoholism,back pain due to sudden lifting of load, casual approach | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Alcohol test Skilled and competant person to carry out the job Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Desciplinary action Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Physical Hazard | Pressure, temperature | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock out tag out Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Physical Hazard | Impact of nitrogen | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock out tag out Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Chemical hazard | Fire due to gas cutting at gas prone area | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Draining and flushing of gas pipeline before welding / gas cutting Usage of CO monitors Skilled and competant person to carry out the job Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Desciplinary action Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Chemical hazard | Gas poisoning | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | usage of CO detector Steam purging of gas pipelines Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Desciplinary action Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Electrical hazard | Electrical shock while welding | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Lock Out Tag Out Use of standard tools & testing equipments Skilled and competant person to carry out the job Work procedure SP 44,SP 46,WI/BF3/05 Skilled Workmen Safety Awareness/traning Use of PPE | 1 | 2 | 2 | Nil
| Stock rod maintenance | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Stock rod maintenance | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Stock rod maintenance | Behavioral Hazards | 3. Casual approach while working. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Stock rod maintenance | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| Stock rod maintenance | Behavioral Hazards | 5. Horseplay | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
12 | V-BELT replacement | Physical Hazard | 1. Noise, vibration, pressure, temperature. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Physical Hazard | 2. Burn injury | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44 ,SP 46,safety awareness training, Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 1. Impingement of rod | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 2. Fall of pipe or tool | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 3. Fall of sparks in eyes, body, ear etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 4. Hitting of drill bit pipe | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 5. Slippage of pipe while handling | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE House keeping | 1 | 2 | 2 | Nil
| V-BELT replacement | Mechanical hazard | 6. Skidding of person due to poor housekeeping. oil spillage, uneven surfaces, etc | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Work procedure WI/BF3/100,SP 44, SP 46,safety awareness training ,Use of PPE House keeping | 1 | 2 | 2 | Nil
| V-BELT replacement | Electrical Hazard | 1. Electric shock due to contact with open end cables & superficially laid underground electric cables. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Electrical shutdown, Work procedure WI/BF3/100, SP 44,SP 46, safety awareness training, | 1 | 2 | 2 | Nil
| V-BELT replacement | Behavioral Hazards | 1. Alcoholism. | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| V-BELT replacement | Behavioral Hazards | 2. Non usage of PPE’s | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| V-BELT replacement | Behavioral Hazards | 3. Casual approach while working | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil
| V-BELT replacement | Behavioral Hazards | 4. Non usage of correct tools | Serious Injury / LTI / MTI | Workmen Contractor employees Supervisors | Training to workmen | 1 | 2 | 2 | Nil