## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 04.04.2022 |  | Revison No. | 2 | Trivial | 1-2
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 2 |  | Revision Date | 09.04.2022 | Acceptable | 3-4
|  | Page No.: | 1 of 1 |  | Dept. | Mechanical | Moderate | 5-9
[5 empty] | Unit: | PP-1 | Substantial | 10-16
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL | [6 empty] | Intolerable | 20-25
Activity: Structural Bridge Replacement | [8 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Mechanical Hazard
1. Trapping between two objects, | Workmen | Physical fitness and competancy of the workmen | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness /traning
Use of PPE
2. Fall of material, hammer, tools, slinged items, bolts, etc. | Workmen | Proper slinging | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
3. Fall of person from platform, | Workmen | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46 | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of safety hardner
4. Entanglement | Workmen | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46 | 1 | 3 | 3 | [5 empty] | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of safety harness
5. Impact of moving / slinged items. | Workmen | Proper slinging | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
6. Fall of material from height such as angles, channels, beams, plates ,bolts ,nuts etc. due to poor housekeeping. | Workmen | Proper slinging | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
7. Failure of sling, D shackle, chain pulley block | Workmen | Use of Certified tools and tackles | 1 | 2 | 2 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
8. Failure of full body harness due to improper clamping, damaged rope, hooking on weak structure | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
9. Skidding of person due to poor housekeeping, oil spillage, uneven surfaces, broken bricks etc | Workmen | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Alloting job as per Healtheness of workmen
| Supervisors | Safety Awareness/traning
Use of PPE
10. Back pain while handling heavy load and improper posture | Workmen | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Deciplinary action
11. Cut injuries from sharp edges of items | Workmen | Testing of the tools at regular interval by external party | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of PPE's
12. Getting trapped / skid material stacked | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
13. Hitting of moving vehicles, and machinery in the plant | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
14. Slipping/Rolling of trolley while loading/unloading | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
15. Falling of cylinders due to improper fixing of protective M.S.chain | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
16. Fall of cylinder trolley due to failure of wheels | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
17. Explosion due to impact on the knob | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
18. Failure of the clutch / brake of hydra / material handling vehicles | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
19. Sliding/rolling of the material from vehicle. | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
20. Impact of moving / slung items, overturning / slipping of steel items. | Workmen /Contract Workmen | SP 44 & on the job traning/instructions | 2 | 2 | 4 | [5 empty] | 0
Usage of standard trolley
Usage of tested/certified cylinder
21. Failure of rope | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
22. Bursting of tyre while moving / during erection | Workmen | Strucral stability checking during erection | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
23. Jamming of the hand while locking the tempo/truck gates. | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
24. Getting trapped below Hydra because of failure of brakes or sudden jerks | Workmen | Strucral stability checking during erection | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
25. Getting trapped between the swing portion & the body of Hydra | Workmen | Strucral stability checking during erection | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
26. Getting hurt because of poor visibility | Workmen | Strucral stability checking during erection | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
27. Impact of other vehicles | Workmen | Strucral stability checking during erection | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//3EPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
30. Skidding of wheel stoppers | Workmen | Strucral stability checking during erection | 1 | 2 | 2 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46
| Supervisors | Safety Awareness/traning
32. Overturning of vehicles due to uneven surfaces | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
33. Overturning due to loosing the centre of gravity. | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
34. Hitting of person while reversing | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
35. Incidents due to poor illumination | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
36. Failure of the workmen basket structure, temporary platform | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
37. Fall of person from height due to unbalance from workmen basket, temporary platform | Workmen /Contract Workmen | SP 44 & on the job traning/instructions | 1 | 2 | 2 | [5 empty] | 0
38. Trapping of the person between basket and structure | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
39. Fall of workmen basket, temporary platforms due to failure of the clamping | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
40. Lifting of the truck due to unstable loading | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
41. Hitting on surrounding structures, while negotiating a turn | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
42. Fall of the Pal finger crane from the truck due to failure of mounting bolt | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
43. Failure of hydraulic system | Workmen /Contract Workmen | Work procedure WI/MAINT//GEPL/18,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
44. Failure of hook of the crane | Workmen /Contract Workmen | Work procedure WI/MAINT/12 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
45. Fall of “falka” of truck during movement. | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
46. Fall of the extended boom from top. | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
47. Damage of overhead structure during marching of crane / hydra | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
48. Hitting / trapping of crane due to improper / non sequential operation | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
49. Bending of chassis due to non levelling of stabilizers | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
50. Failure of stabilizers | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
51. Failure of crane / chassis due to non levelling of crane platform with water level | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
52. Hitting of the boom due to fast operation. | Workmen /Contract Workmen | SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
53. Improper operation due to improper signalling. | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
54. Scaffold collapse caused by instability or over loading | Workmen /Contract Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
55. Incident due to usage of mobile while driving / operation of crane / hydra / Palfinger/ Hiab basket | Workmen | Keeping distance of cylinder from source of fabrication | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
56. Trapping due to Improper jacking during crane maintenance | Workmen | Use of flashback arrestor | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
57. Fire due to fall of sparks welding / gas cutting | Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
58. Back fire during gas cutting | Workmen | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Safety Awareness/traning
Supervisors
59. Failure of welding hook due to improper / inadequate welding | Workmen/Subcontractor on the Job | Work procedure WI/MAINT/12,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
Safety Awareness/traning
60. Failure of welding hook due to welding on hard faced plates / unknown plates | Workmen | Work procedure WI/MAINT/NPP/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
61. Radiation due to welding | Workmen | Work procedure WI/MAINT/NPP/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Physical hazard:
Temperature | Workmen | Work procedure WI/MAINT/NPP/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Pressure due to failure of air system/Hydraulic pressurized system during process | Workmen /Contract Workmen | Work procedure WI/MAINT/NPP/30,SP 44,SP 46 | 2 | 2 | 4 | [5 empty] | 0
Chemical Hazard |  | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
1.Fire & Explosion | Workmen | Ensuring availability of wet gunny bag on DA cylinder | 2 | 2 | 4 | [5 empty] | 0
| Contractor employees | Keeping distance of cylinder from source of fabrication |  |  |  | Nil
| Supervisors | Checking of cylinder nozzle leakage during issue of cylinder
Usage of ball type seal regulator to ensure complete seaing for LPG
Skilled Workmen
Safety Awareness/traning
Use of PPE
Electrical Hazard
Electric shock from overhead lines or welding | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Deciplinary action
Short circuit due to failure of electrical system | Workmen | Testing of the tools at regular interval by external party | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Electric shock from battery terminal | Workmen | Testing of the tools at regular interval by external party | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Behavioural Hazard:
Non use of PPE: | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 1 | 2 | 2 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Alcoholism | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 1 | 3 | 3 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Alcohol test while entry
Improper housekeeping | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Height phobia | Workmen | Height Permit and height test | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46
| Supervisors | Skilled Workmen
Safety Awareness/training
Use of PPE
Disciplinary action
Overconfidence | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Negligence | Workmen | Work procedure WI/MAINT/GEPL/30,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  |  |  | 0
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Note : (a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in QEHS/SP/41 of QEHS System Procedure.
Signature of the Assessor:-
Date:-09.04.2022