## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 19.07.2023 |  |  |  |  | Acceptable | 3-4 | Revision No. | 2
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 3 |  |  |  |  | Moderate | 5-9 | Revision Date | 07.12.2022
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical
[8 empty] | Intolerable | 20-25 | Unit | PP1
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: Valve Overhauling | [8 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Mechanical Hazard
Fall of valve on feet, hand while shifting | Workmen | Proper slinging | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Entanglement | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 |  |  |  | 2 | 2 | 4
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of safety harness
Fall of valve while keeping in vertical | Workmen | Proper slinging | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Injury while using chisel | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Fall of spare parts while overhauling | Workmen | Proper slinging | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46
| Supervisors | Safety Awareness/traning
Use of PPE
Chips entering in eyes while chipping | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Back pain while handling heavy load and improper posture | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Physical hazard:
1. Burn injury from gas cutting operation | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Electrical Hazard
Electric shock while re-building on broken parts | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Deciplinary action
Behavioural Hazard:
Non use of PPE: | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Alcoholism | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Alcohol test while entry
Improper housekeeping | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Overconfidence | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Negligence | Workmen | Work procedure WI/MAINT/GEPL/4,SP 44,SP 46 | 2 | 2 | 4 | Nil |  |  | 2 | 2 | 4
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Name and signature of the Assessor: | DEEPAK KUDALKAR
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Name and signature of the Workmen: Sugriv Verma
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation | [5 empty] | Reviewed Date:-05.09.2023

## Sheet1 (hidden)
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 04.04.2022 |  |  |  |  | Acceptable | 3-4 | Revision No. | 3
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 2 |  |  |  |  | Moderate | 5-9 | Revision Date | 05.09.2023
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical
[8 empty] | Intolerable | 20-25 | Unit | PP1
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: Maintenance of pumps | [8 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
[5 empty] | 0 | Nil |  |  |  |  | 0
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Name and signature of the Assessor: | DEEPAK KUDALKAR
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Name and signature of the Workmen:
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation | [5 empty] | Reviewed Date:-05.09.2023