## Monthly Progess of Obj. & Tar
| VEDANTA LIMITED – VALUE ADDED BUSINESS |  | Format No.: | FRMT/MR/15 |  | Department Use only
| INTEGRATED MANAGEMENT SYSTEM |  | Revision Date: | 04.04.2022 |  | Revision No. | 1 | [19 empty] | QMS
| Monthly Progress of Objective & Target |  | Revision No.: | 1 |  | Review Date | 04.04.2023 | [19 empty] | EMS
|  |  | Page No.: | 1 of 1 |  | Dept | mech | [19 empty] | OH&S
[6 empty] | Unit | PP2 | [19 empty] | EnMS
FinYear | Sr. no | Title | Owner | HOD | BusinessUnit | Location | Department | System | UOM | Base line | Target | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | YTD ACTUAL Till Jan 21 | STATUS | REASON FOR DEVIATION
FY 23-24 | 1 | Ensure 100% safe working provision to eliminate unsafe condition in TG bleed line surronding . PP2 FTY 23-24 | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | OHSMS | PERCENT% | 0 | 100%
FY 23-24 | 2 | To ensure 100% availability of river water system. PP2 FTY 23-24 | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | QMS | meters | 40% | 100%
FY 23-24 | 3 | Improve PP2 plant availability from 97.6% to 99.5%, excluding annual shutdown and planned shutdown | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | QMS | PERCENT% | 97.6% | 99.5%
FY 23-24 | 4 | Improve PP1 plant availability from 95.54% to 99.5%, excluding annual shutdown and planned shutdown | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | QMS | PERCENT% | 95.54% | 99.5%
FY 23-24 | 5 | Provision of goggle valve in BFG blower system to improvement plant availability by 5 % in annuam | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | QMS | PERCENT% | 0 | 5%
FY 23-24 | 6 | Minimise river water consumption from 120 m3/hr to 30 m3/hr on daily basis during rainy season from mining pit water PP1 FTY 23-24 | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | EMS | M3/Hr | 0 | 30 m3/hr
FY 23-24 | 7 | Oil Recovery in Power Plant from 58.1% FTY 22-23 to 80% FTY 23-24 PP | Chethan K | Deepak Kudalkar | VAB | PP | Mechanical Maintenance | EMS | PERCENT% | 58.1% | 80%

## MP
|  | VEDANTA LIMITED – VALUE ADDED BUSINESS |  | Format No.: | FRMT/MR/14 |  | Department Use only
|  | INTEGRATED MANAGEMENT SYSTEM |  | Revision Date: | 04.04.2022 |  | Revision No. | 1
|  | Management Programme |  | Revision No.: | 1 |  | Review Date | 04.04.2023
|  |  |  | Page No.: | 1 of 1 |  | Dept | Mechanical
[7 empty] | Unit | Power Plant
ManagmntProgramID | Sr_no | Title | Action_plan | Responsibility | Planned_Start_Date | Planned_End_Date | Actual_Start_Date | Actual_End_Date | Remarks | Recources_required | Target | Performance_indicator | ReviewedBy | MP_statusUpdate
| 1 | Ensure 100% safe working provision to eliminate unsafe condition in TG bleed line surronding . PP2 FTY 23-24 | Provide Permanent structural Working Platformtubine bleed line | Chethan K | 2023-05-02 | 2023-08-30 | 2023-05-03 |  |  |  |  | Job progres tracking & Completion | Head O & M PP
|  |  | Provide Permanent structural Working Platform tubine bleed QCNRV | Chethan K | 2023-05-02 | 2023-08-30 | 2023-05-03
|  |  | Provide Permanent structural Working Platform tubine warm up vent valve | Chethan K | 2023-05-02 | 2023-08-30 | 2023-05-03
| 2 | To ensure 100% availability of river water system. PP2 FTY 23-24 | Replacement of RWP pump | Chethan K | 2023-04-01 | 2024-02-25 | 2023-04-01 |  |  | Pump procurement under CAPEX early iniation, piping material |  | Project Completion | Head O & M PP
|  |  | Replacment of RWP priming chamber suction, discharge pipe lines | Chethan K | 2023-04-01 | 2024-02-25 | 2023-04-01
|  |  | Interconnection of both PP - RWP discharge interconnection near pump station | Chethan K | 2023-04-01 | 2024-02-25 | 2023-04-01
|  |  | Interconnection of both PP - RWP discharge interconnection near Plant CT cell | Chethan K | 2023-04-01 | 2024-02-25 | 2023-04-01
| 3 | Improve PP2 plant availability from 97.6% to 99.5%, excluding annual shutdown and planned shutdown | Replacement of both boiler critical IBR valves, | Chethan K | 2023-04-01 | 2023-12-30 | 2023-04-01 |  |  |  |  | Project Completion | Head O & M PP
|  |  | Annual Thickness mappping of Boiler Tubes for inacessable area on sample basis | Chethan K | 2023-04-01 | 2023-12-30 | 2023-04-01
| 4 | Improve PP1 plant availability from 95.54% to 99.5%, excluding annual shutdown and planned shutdown | Replacement of both boiler critical pressure parts and critical IBR valves | A Nabar | 2023-04-01 | 2024-03-30 | 2023-04-01
|  |  | Turbine stoppage root cause identification and impliment all CAPA points | A Nabar | 2023-04-01 | 2024-08-30 | 2023-04-01
|  |  | Annual Thickness mappping of Boiler Tubes for inacessable area on sample basis | A Nabar | 2023-04-01 | 2024-03-30 | 2023-04-01 |  |  |  |  | Project Completion | Head O & M PP
Replacement of MCW circuit valves
| 5 | Provision of goggle valve in BFG blower system to improvement plant availability by 5 % in annuam | BFG Blower 1 - Goggle valve with proper working platform | A Nabar | 2023-04-01 | 2023-10-30 | 2023-04-01 |  |  |  |  | Inspection of RW System Quarterly & Tracking | Head O & M PP
|  |  | BFG Blower 2 - Goggle valve with proper working platform | A Nabar | 2023-04-01 | 2023-10-30 | 2023-04-01
| 6 | Oil Recovery in Power Plant from 58.1% FTY 22-23 to 80% FTY 23-24 PP | Collection of waste oil from all areas and record keeping on quarterly basis | A Nabar | 2023-04-01 | 2024-03-30 | 2023-04-01 |  |  |  |  | Project Completion | Head O & M PP
|  |  | Quarterly return of oil to store | A Nabar | 2023-04-01 | 2024-03-30 | 2023-04-01
|  |  | Quarterly tracking of new oil received and waste oil returned to store | A Nabar | 2023-04-01 | 2024-03-30 | 2023-04-01
BACK