## RA-47 REFRACTORY JOBS
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 15.04.2020
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 1 |  |  |  | Trivial | 1-2
|  | Page No.: | 1 of 1 |  | REV. |  | Acceptable | 3-4
[5 empty] | Unit: | NPPL | Moderate | 5-9
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL | [6 empty] | Substantial | 10-16
Activity:Refractory Jobs in Boiler | [6 empty] | Intolerable | 20-25
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO.
Mechanical Hazard
Fall of man/ material, from height | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 4 | 8 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of safety harness
Permit to work at hieight
Entanglement | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46, usage of basket | 2 | 3 | 6
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Usage of safety harness
Impact of moving / sling items | Workmen /Contract Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46, usage of basket | 2 | 3 | 6
| Usage of standard trolley | Skilled Workmen
| Usage of tested/certified cylinder | Safety Awareness/traning
Use of PPE
Physical Hazard
Suffocation | Workmen | Using multigas monitor in confined spaces | 2 | 4 | 8 | Nil
| Contractor employees | Vedanta Safety Standard to follow
| Supervisors | Work procedure WI/MAINT/NPP/47,SP 44,SP 46
Training, awareness,
Water Pressure | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 3 | 6 | Nil
| Contractor employees | Safety Awareness/traning
| Supervisors | Use of PPE
Health Hazard
CO gas poisoning | Workmen | Online CO monitor and Handheld CO mointor to be used | 2 | 4 | 8 | Nil
| Contractor employees | U-seal has to be filled
| Supervisors | Work procedure WI/MAINT/NPP/47,SP 44,SP 46
Safety Awareness/traning
Use of PPE
Electrical Hazard
Electric shock | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 3 | 6 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/traning
Use of PPE
Deciplinary action
Behavioural Hazard:
Non use of PPE: | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 3 | 3 | 9 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Alcoholism | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 1 | 3 | 3 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Alcohol test while entry
Improper housekeeping | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 3 | 6 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Improper Body positioning | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 2 | 4 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Overconfidence | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 3 | 6 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Disciplinary action
Negligence | Workmen | Work procedure WI/MAINT/NPP/47,SP 44,SP 46 | 2 | 3 | 6 | Nil
| Contractor employees | Skilled Workmen
| Supervisors | Safety Awareness/training
Use of PPE
Disciplinary action
Note : (a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in QEHS/SP/41 of QEHS System Procedure.
Signature of the Assessor:-
Date:-30.05.2020