## Risk Assessment And Control
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only |  | COMPLETED
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 14.11.2022 |  |  |  |  | Acceptable | 3-4 | Revision No. | 6 | IN PROGRESS
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 1 |  |  |  |  | Moderate | 5-9 | Revision Date | 15.11.2022 | PENDING
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical Maintenance
[8 empty] | Intolerable | 20-25 | Unit | PID II
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity:De Dusting Maintenance |  | RISK LEVEL WITH EXISTING CONTROL | [6 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Physical Hazard
1. Noise, vibration, pressure, temperature. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
2. Impact of pressurized air/nitrogen on the body. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
3. Fire and Explosion. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| Contractor employees | [7 empty] | 1 | 2 | 2
Supervisors
4. Slip and fall due to oil spillage. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
5. Slipping due to accumulation of graphite/poor housekeeping. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE | 2 | 1 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
Mechanical Hazard
1. Fall of material Casing, Assembly due to irregular size | Workmen | Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
2. Crushing of person while lifting the material & fall | Workmen | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| Contractor employees | [7 empty] | 1 | 2 | 2
| Supervisors | Safety Awareness /traning
Use of PPE
3. Fall while installation of Equipment. | Workmen | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
| Supervisors | Use of safety belts
[9 empty] | 1 | 2 | 2
4. Trapping of person during the fall of material from height | Workmen | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
Contractor employees
Supervisors
[9 empty] | 1 | 2 | 2
5. Fall of material due to mass & stability | Workmen | Proper slinging,safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| Contractor employees | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | [6 empty] | 1 | 2 | 2
Supervisors
6. Failure of lifting machines, handling machines such as chain pulley block, sling, D shackle etc | Workmen | Tesing of tools at regular interval by external patry,Proper slinging,safety awareness/training,skilled workmen | 1 | 2 | 2 | Nil
| Contractor employees | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE
| Supervisors | [7 empty] | 1 | 2 | 2
7. Back Pain due to sudden or heavy load like vane feeder, motor, scrapper conveyor gear box. | Workmen | Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil
| Contractor employees | [7 empty] | 1 | 2 | 2
Supervisors
8. Cut from sharp edges of items. | Workmen | Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | proper slinging of items,Skilled workmen,Use of PPE,
Supervisors
9. Non use of PPE’s while carrying out the activity. | Workmen | proper slinging of items,Skilled workmen,Use of PPE, | 1 | 2 | 2 | Nil
| Contractor employees | Usage of certified Lifting tools & tackles,Work procedure WI/BF3/11,SP 44,,Safety awareness , Safety treaining, Use of PPE | [6 empty] | 1 | 2 | 2
Supervisors
10. Hitting of slinged items on existing structures / running machinery. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE, timely inspection of lifting equipments. | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | proper slinging of items,Skilled workmen,Use of PPE,
Supervisors
11. Fall of person inside hopper while bags checking. | Workmen | Work procedure WI/BF3/11,SP 44,SP 46,Safety awareness , Safety treaining, Use of PPE, timely inspection of lifting equipments. | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
| Contractor employees | proper slinging of items,Skilled workmen,Use of PPE,
Supervisors
Electrical hazard
1. Electric shock due to contact with open end cables & superficially laid underground electric cables. | Workmen | Work procedure WI/BF3/24,SP 44,SP 46,Safety awareness , Safety treaining, Electrical shutdown | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
Behavioral Hazards
1. Alcoholism. | Workmen | Training to workmen | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
2. Non usage of PPE’s | Workmen | Training to workmen | 1 | 2 | 2 | Nil
| Contractor employees | [7 empty] | 1 | 2 | 2
Supervisors
3. Casual approach while working. | Workmen | Training to workmen | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
4. Non usage of correct tools | Workmen | Training to workmen | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
5. Horseplay | Workmen | Training to workmen | 1 | 2 | 2 | Nil |  |  | 1 | 2 | 2
Contractor employees
Supervisors
Note : (a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in QEHS/SP/41 of QEHS System Procedure.
Signature of the Assessor:-
Date:- 15.11.2022