## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only |  | COMPLETED
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 04.04.2022 |  |  |  |  | Acceptable | 3-4 | Revision No. | 4 | IN PROGRESS
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 2 |  |  |  |  | Moderate | 5-9 | Revision Date | 14.08.2022 | PENDING
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical
[8 empty] | Intolerable | 20-25 | Unit | MCD
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: |  | RISK LEVEL WITH EXISTING CONTROL | [6 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Mechanical Hazard (falling, Trapping) | Contractor Workmen | 1) Barricading with work in progress board at truck loading side | 1 | 3 | 3 | hard barricading |  | COMPLETED | 1 | 3 | 3
|  | 2) Shutdown of related equipment as per wi 26 | 1 | 3 | 3 | Existing controls are monitored |  | IN PROGRESS | 1 | 3 | 3
Non use of PPE: Resulting in fall | Contract workman | Training, awareness, Inspection & Disciplinary action | 1 | 3 | 3 | Display of safety posters |  |  | 1 | 3 | 3
Improper housekeeping | Company, contract employees & visitors | Training,Inspection | 1 | 3 | 3 | Nil |  | PENDING | 1 | 3 | 3
Alcolism | Contract workman | Training, awareness, Inspection & Disciplinary action | 1 | 3 | 3 | Nil |  |  | 1 | 3 | 3
Height fobia | Contract workman | Training,Inspection | 1 | 3 | 3 | Nil |  |  | 1 | 3 | 3
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Signature of the Assessor:-
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Reviewed Date:-
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation