## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/11 |  |  |  |  | Trivial | 1-2 | Departmental Use only |  | COMPLETED
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 19.07.2023 |  |  |  |  | Acceptable | 3-4 | Revision No. | 5 | IN PROGRESS
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 3 |  |  |  |  | Moderate | 5-9 | Revision Date | 14.08.2022 | PENDING
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical
[8 empty] | Intolerable | 20-25 | Unit | MCD
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: |  | RISK LEVEL WITH EXISTING CONTROL | [6 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Water Ingress | Company/ Contract workman | Electrical & Mechanical isolation of pump & valves, Take 5, Training and Awareness, | 1 | 4 | 4 | Nil |  |  | 1 | 4 | 4
Electrical shock | Company/ Contract workman | Electrical isolation, Take 5, Training and Awareness, | 1 | 5 | 5 | provide training of confined space entry before staring work |  |  | 1 | 5 | 5
Impact, Entrapment, Entanglement, Hit, Cut, Slip, trip | Company/ Contract workman | Use of PPE, Take 5, Training and Awareness Use of certified chain blocks & slings, cordoning/ baricading of area, Taking protocol /work permits from Production dept. | 1 | 3 | 3 | Nil |  |  | 1 | 3 | 3
Fall | Company/ Contract workman | Use of PPE, Take 5, Training and Awareness, Handrailing with toe-guard or full body harness | 1 | 4 | 4 | Nil |  |  | 1 | 4 | 4
Fire and explosion, fumes. | Company/ Contract workman | Remove/ cover combustible material, fire extinguisher, fire hydrant point | 2 | 3 | 6 | provide exhaust fan for removing unburned gases |  |  | 2 | 3 | 6
Poor workplace design & confned space | Company/ Contract workman | Use of PPE, Take 5, Training and Awareness, valid confined pass,attendant/ stand-by person, rescue team, gas analyser to montior O2 level | 3 | 3 | 9 | Nil |  |  | 3 | 3 | 9
Human behaviour aspect: • Alcoholism. • Casual approach. • Horse play. • Non usage of PPE’s • Improper Housekeeping • Height Phobia | Contract workman | Alcoholism: Screening at gate Height Phobia: Issue of Height pass Counselling, Warnings & Suspension | 3 | 2 | 6 | Nil |  |  | 3 | 2 | 6
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Name and signature of the Assessor: | Sachin Undre
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Name and signature of the Workmen: Balgo Sinari
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation | [5 empty] | Reviewed Date:- | 15.09.2023