## Risk Assessment And Control_1
| VEDANTA LIMITED – VALUE ADDED BUSINESS | Format No.: | FRMT/MR/ |  |  |  |  | Trivial | 1-2 | Departmental Use only |  | COMPLETED
| INTEGRATED MANAGEMENT SYSTEM | Revision Date: | 14.11.2022 |  |  |  |  | Acceptable | 3-4 | Revision No. | 7 | IN PROGRESS
| RISK ASSESSMENT AND RISK CONTROL | Revision No.: | 0 |  |  |  |  | Moderate | 5-9 | Revision Date | 14.11.2022 | PENDING
|  | Page No.: | 1 of 1 |  |  |  |  | Substantial | 10-16 | Dept | Mechanical
[8 empty] | Intolerable | 20-25 | Unit | SP
FORMAT FOR RISK ASSESSMENT AND RISK CONTROL
Activity: Chill Fan and DD Fan Bearing |  | RISK LEVEL WITH EXISTING CONTROL | [6 empty] | RISK LEVEL AFTER OPPORTUNITIES IMPLEMENTATION
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
HAZARDS | PERSONNELS AT RISK | EXISTING CONTROL MEASURES | LIKELY HOOD OF HARM | SEVERITY OF HARM | RISK LEVEL | OPPORTUNITIES (PROPOSED CONTROL MEASURES,IF ANY) | PROGRAMME REF. NO. | STATUS | REVISED LIKELY HOOD OF HARM | REVISED SEVERITY OF HARM | REVISED RISK LEVEL
Mechanical Hazard
1. Trapping of person due to improper laying of welding cable, hoses | Workmen on job | Work Procedure |  |  |  |  | -
| Contract Workmen | SP44E & F | 4 | 1 | 4 | Nil
| Supervisors | On the Job training
2. Material handling hazards | Workmen | Work procedure SP 44,WI/SP/MAINT/13 | 4 | 1 | 4 | Nil
| Contractor employees | Safety Awareness/training
Use of PPE
On the Job training
3. Failure of lifting tools and tackles | Workmen | Skilled workmen | 4 | 1 | 4 | Nil
| Contractor employees | Work procedure WI/SP/MAINT/13,SP44 E & F
| Supervisors | Safety Awareness/training
proper slinging arrangement
Physical hazards
1. Falling of person from height. | Workmen | Use of full body harness |  |  |  | Nil
| Contractor employees | Work procedure WI/MAINT/103 | 4 | 1 | 4
Safety Awareness/traning
2. Burn injury to workmen while gas cutting welding | Workmen | Work procedure SP44 E & F |  |  |  | Nil
| Contractor employees | on the job training | 4 | 1 | 4
| Supervisors | Use of PPE
3. Burn injury due to contact with hot surface | Workmen | Work procedure SP44 E & F |  |  |  | Nil
| Contractor employees | on the job training | 4 | 1 | 4
| Supervisors | Use of PPE
Electrical hazard
1. Electric shock due to welding | Workmen | Welding checklist | 3 | 1 | 3 | Nil
| Contractor employees | Work procedure SP 44E & F
| Supervisors | Safety Awareness/traning
Use of PPE
Behavioural Hazards
1. Person working under the influence of alcohol | Workmen | random checking of alcohol level | 4 | 1 | 4 | Nil
Contractor employees
Supervisors
2. Violation of work instructions | Workmen | pep talks | 4 | 1 | 4 | Nil
| Contractor employees | on the job training
Supervisors
3. Casual approach | Workmen | pep talks | 4 | 1 | 4 | Nil
| Contractor employees | on the job training
Supervisors
4.Person not wearing PPE’s | Workmen | pep talks | 4 | 1 | 4 | Nil
| Contractor employees | on the job training
| Supervisors | Work procedure SP 44E & F
5. Horseplay | Workmen | pep talks | 4 | 1 | 4 | Nil
| Contractor employees | on the job training
Supervisors
Note:
(a) For filling column (1) information recorded in the format FRMT/MR/10 is used.
(b) For filling column 4,5 use Appendix A and FOR COLUMN (6) USE Table 1in VL/IMS/VAB/SP41 of System Procedure. | [5 empty] | Signature of the Assessor:-
C) Status(9) Select the drop down for updating status of oppurtunities implementation (Completed /In Progress/ Pending) | [5 empty] | Reviewed Date:-14.11.2022
d) Revised Likelyhood(10)/Revised Severity of Harm(11)/Risk Level(12) to be updated based on oppurtunity implementation